## Sheet1
COST ESTIMATE
Project Name: Getaway Groceries - Online Grocery Store |  |  | Date: 05/23/2020
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 100 | 22 | 2200 |  |  | 0 | 2200 |  | 2200
2. Planning | 50 | 43 | 2150 |  |  | 0 | 2150 |  | 2150
3. Executing |  |  | 0 |  |  | 0 | 0 |  | 0
3.1 Course design and development |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.1 Supplier management training | 100 | 33 | 3300 | 200 | 100 | 20000 | 23300 | 50000 | 73300
3.1.2 Negotiating skills training | 100 | 25 | 2500 | 130 | 120 | 15600 | 18100 | 20000 | 38100
3.1.3 Project management training | 70 | 17 | 1190 | 120 | 130 | 15600 | 16790 | 20000 | 36790
3.1.4 Software applications training | 50 | 22 | 1100 | 120 | 80 | 9600 | 10700 | 25000 | 35700
3.2 Course administration | 100 | 11 | 1100 | 90 | 70 | 6300 | 7400 | 40000 | 47400
3.3.Course evaluation | 120 | 17 | 2040 |  |  | 0 | 2040 |  | 2040
3.4 Stakeholder communications | 100 | 20 | 2000 |  |  | 0 | 2000 |  | 2000
4. Monitoring and Controlling | 200 | 18 | 3600 |  |  | 0 | 3600 |  | 3600
5. Closing | 10 | 33 | 330 |  |  | 0 | 330 |  | 330
Subtotal | [8 empty] | 243610
Reserves |  |  | 0 |  |  | 0 | 0 |  | 24361
Total | 1000 |  | 21510 | 660 | 500 | 67100 | 86250 | 155000 | 267971
Assumption: We are expecting around 250,000 $ with a reserve of 10 % overall cost and our total budget is 267,971 $