## WBS
Team Project Draft Schedule
Team Project Draft Schedule
Only enter hours for the lowest level tasks (verb phrases, indented farthest right). Have draft schedule ready for PR1 and update info and use to create your Gantt chart for PR 2.
PR=Progress Report
|  |  | Total hours-> | 56 | 58 | 63 | 53 | 0 | 230 | 35 | 35 | 34 | 31 | 0 | 135
Major tasks | Start Date | End Date | Responsible | Estimated Hours per person |  |  |  |  | Total | Actual Hours |  |  |  |  | Total
|  |  |  | A | B | C | D | E | Est. Hours | A | B | C | D | E | Act. Hours
1.1 Initiating |  |  |  | Tarun | Alekhya | Sai Rohith | Navya |  | Est. Hours | Tarun | Alekhya | Sai Rohith | Navya |  | Act. Hours
1.1.1 Project charter (PR1) | 2020-05-12 08:00 | 2020-05-12 17:00 | 10 | 4 | 3 | 2 | 1 |  | 10 | 4 | 3 | 2 | 1 |  | 10
1.1.2 Kick-off meeting (PR1) | 2020-05-13 08:00 | 2020-05-13 17:00 | 5 | 2 | 1 | 1 | 1 |  | 5 | 2 | 1 | 1 | 1 |  | 5
1.1.3 Team MBTI summary (PR1) | 2020-05-13 08:00 | 2020-05-13 17:00 | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
1.1.4 Sponsor feedback (PR1) | 2020-05-14 08:00 | 2020-05-14 17:00 | 4 | 1 |  | 1 | 2 |  | 4 | 1 |  | 1 | 2 |  | 4
1.1.5 Google site initial set-up (PR1) | 2020-05-14 08:00 | 2020-05-14 17:00 | 0 | [5 empty] | 0 | [5 empty] | 0
1.2 Planning |  |  | 2 | 1 | 1 |  |  |  | 2 | 1 | 1 |  |  |  | 2
1.2.1 Draft scope statement (PR1) | 2020-05-15 08:00 | 2020-05-15 17:00 | 12 | 3 | 3 | 4 | 2 |  | 12 | 3 | 3 | 4 | 5 |  | 15
1.2.2 Team contract (PR1) | 2020-05-15 08:00 | 2020-05-15 17:00 | 5 | 2 | 2 |  | 1 |  | 5 | 2 | 2 |  | 1 |  | 5
1.2.3 Excel draft schedule (PR1) | 2020-05-16 08:00 | 2020-05-16 17:00 | 6 | 1 | 4 | 1 |  |  | 6 | 1 | 4 | 1 |  |  | 6
1.2.4 Gantt chart (PR2) | 2020-05-16 08:00 | 2020-05-16 17:00 | 7 | 2 | 1 | 3 | 1 |  | 7 | 2 | 1 | 3 | 1 |  | 7
1.2.6 Updated scope statement (PR2) | 2020-05-17 08:00 | 2020-05-17 17:00 | 4 | 1 | 1 | 1 | 1 |  | 4 | 1 | 1 | 1 | 1 |  | 4
1.2.5 Additional sponsor feedback (PR2) | 2020-05-17 08:00 | 2020-05-17 17:00 | 5 | 1 | 2 | 1 | 1 |  | 5 | 1 | 2 | 1 | 1 |  | 5
1.3 Executing |  |  | 5 | 1 | 1 | 2 | 1 |  | 5 | 1 | 1 | 2 | 1 |  | 5
1.3.1 Communications |  |  | 12 | 3 | 3 | 3 | 3 |  | 12 | 5 | 5 | 5 | 5 |  | 20
1.3.1.1 Document team meetings | 2020-05-18 08:00 | 2020-05-18 17:00 | 5 | 2 | 1 | 1 | 1 |  | 5 | 2 | 1 | 1 | 1 |  | 5
1.3.1.2 Document sponsor meetings/feedback | 2020-05-19 08:00 | 2020-05-19 17:00 | 4 | 1 | 1 | 1 | 1 |  | 4 | 1 | 1 | 1 | 1 |  | 4
1.3.1.3 Update Google site | 2020-05-20 08:00 | 2020-05-20 17:00 | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
1.3.2 Main deliverable 2 |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  |  | 2
Task 1 | 2020-05-21 08:00 | 2020-05-21 17:00 | 10 | 1 | 3 | 3 | 3 |  | 10 | 1 | 3 | 3 | 3 |  | 10
Task 2 | 2020-05-21 08:00 | 2020-05-21 17:00 | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
Task 3 | 2020-05-21 08:00 | 2020-05-21 17:00 | 4 |  | 2 | 2 |  |  | 4 |  | 2 | 2 |  |  | 4
1.3.3 Main deliverable 3 | 2020-05-22 08:00 | 2020-05-22 17:00 | 3 |  |  | 1 | 2 |  | 3 |  |  | 1 | 2 |  | 3
Task 1 | 2020-05-22 08:00 | 2020-05-22 17:00 | 6 | 2 | 2 | 1 | 1 |  | 6 | 2 | 2 | 1 | 1 |  | 6
Task 2 | 2020-05-22 08:00 | 2020-05-22 17:00 | 3 | 1 |  | 2 |  |  | 3 | 1 |  | 2 |  |  | 3
Task 3 | 2020-05-23 08:00 | 2020-05-23 17:00 | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
etc. | 2020-05-23 08:00 | 2020-05-23 17:00 | 2 |  | 1 |  | 1 |  | 2 |  | 1 |  | 1 |  | 2
1.4 Monitoring and Controlling |  |  | 4 | 2 |  | 2 |  |  | 4 | 2 |  | 2 |  |  | 4
1.4.1 Progress report 1 (PR1) |  |  | 15 | 3 | 4 | 4 | 4 |  | 15
1.4.1.1 Fill out progress report template | 2020-05-24 08:00 | 2020-05-24 17:00 | 7 | 3 |  | 3 | 1 |  | 7
1.4.1.2 Assemble all documents for PR1 | 2020-05-24 08:00 | 2020-05-24 17:00 | 3 |  | 1 |  | 2 |  | 3
1.4.1.3 Prepare and practice presentation | 2020-05-24 08:00 | 2020-05-24 17:00 | 4 | 2 |  | 2 |  |  | 4
1.4.1.5 Post all info online | 2020-05-25 08:00 | 2020-05-25 17:00 | 1 |  |  |  | 1 |  | 1
1.4.2 Progress report 2 (PR2) |  |  | 1 |  |  |  | 1 |  | 1
1.4.2.1 Fill out progress report template | 2020-05-25 08:00 | 2020-05-25 17:00 | 9 |  | 3 | 3 | 3 |  | 9
1.4.2.2 Prepare est. vs. actual hours summary | 2020-05-25 08:00 | 2020-05-25 17:00 | 7 | 2 |  | 4 | 1 |  | 7
1.4.2.3 Assemble all documents for PR2 | 2020-05-26 08:00 | 2020-05-26 17:00 | 1 |  | 1 |  |  |  | 1
1.4.2.4 Prepare and practice presentation | 2020-05-26 08:00 | 2020-05-26 17:00 | 1 |  |  | 1 |  |  | 1
1.2.2.5 Post all info online | 2020-05-26 08:00 | 2020-05-26 17:00 | 2 |  |  | 1 | 1 |  | 2
1.4.3 Other monitoring and controlling | 2020-05-27 08:00 | 2020-05-27 17:00 | 3 | 1 |  | 2 |  |  | 3
1.5 Closing |  |  | 3 |  | 2 |  | 1 |  | 3
1.5.1 Project notebook | 2020-05-28 08:00 | 2020-05-28 17:00 | 14 | 3 | 4 | 3 | 4 |  | 14
1.5.1.1 Assemble all documents for notebook | 2020-05-29 08:00 | 2020-05-29 17:00 | 14 | 3 | 4 | 4 | 3 |  | 14
1.5.1.2 Receive project completion form from sponsor | 2020-05-30 08:00 | 2020-05-30 17:00 | 6 | 2 | 2 |  | 2 |  | 6
1.5.1.3 Prepare final report | 2020-05-31 08:00 | 2020-05-31 17:00 | 3 | 1 | 1 | 1 |  |  | 3
1.5.1.4 Prepare and practice final presentation | 2020-06-01 08:00 | 2020-06-01 17:00 | 5 | 1 |  | 2 | 2 |  | 5
1.5.1.5 Post all info online | 2020-06-02 08:00 | 2020-06-02 17:00 | 5 | 2 | 2 | 1 |  |  | 5
1.5.1.6 Final presentation completed (milestone) | 2020-06-04 08:00 | 2020-06-04 17:00 | 2 |  | 1 |  | 1 |  | 2

## Comments
Remember that a WBS is a deliverable-oriented grouping of ALL the work you will do for your project.
For class projects, only the executing section should be different from this template. Decide what the
main deliverables are for your project under executing, the break them down into specific tasks.
The Planning section is for project planning. If one of your deliverables is some other type of plan, put it under Executing

## Gantt Chart
Tasks | Major tasks | Start Date | End date | Working days | Task
1 | 1. Initiating | 2020-05-12 | 2020-05-14 | 2 | 1
2 | 2. Planning | 2020-05-15 | 2020-05-17 | 2 | 2
3 | 3. Communications | 2020-05-18 | 2020-05-20 | 2 | 3
4 | 4. Main deliverables | 2020-05-21 | 2020-05-23 | 2 | 8
5 | 5. Monitoring and Controlling | 2020-05-24 | 2020-05-27 | 3 | 6
6 | 6. Closing | 2020-05-28 | 2020-06-04 | 7 | 7
1. Initiating
2. Planning
3. Communications
4. Main deliverables
5. Monitoring and Controlling
6. Closing